## Sheet1
Start Date | Finish Date | Project Phase | Activities | Result
2017-09-05 | 2017-09-10 | Preliminary Planning and Discussion | Discuss Project Scope, Potential Services, Obtain workable data set | Finalized project idea w/ potential functionality
2017-09-10 | 2017-09-20 | Requirements Elicitation and Validations | Plan user stories, create use case diagrams, evaluate and prioritize risk factors | Finalized project user stories and services for system
2017-09-20 | 2017-10-11 | Sprint 1 | Construct UML domain class diagrams, sequence diagrams,performed environment setup and created architecture as base to work on also finalised and cleaned dataset. | Finalized diagrams to represent the project and aid in the design phase and created a base architecture for everyone to work on and clean dataset.
2017-10-12 | 2017-10-27 | Sprint 2 | construction of recommendation engine to deal with user story 1 and database | Finalized recommendation source code and performed qualification to test results.Databse created.
2017-10-28 | 2017-11-09 | Sprint 3 | construction of recommendation engine to deal with user story 2 | Performed qualification on code to validate generated results
2017-10-27 | 2017-11-18 | Sprint 4 | Construction of web interface user story 3,4, Integration | Finalized web application that interacts with the database and recommendation engine to produce the functional and nonfunctional requirements.
2017-11-18 | 2017-11-25 | Finalization and Consolidation | Finalize all documentation, organize and consolidate deliverables
USER STORIES